## Sheet1
This is a sample project schedule with a fixed launch date and scope, for a company with a straightforward migration path and a small group of users. In this example, the time to go live is one month from the start date, with a launch date of October 15, 2015. There are 2 weeks of post-launch activities following the launch before the project officially closes.
# | Task name | Owner | Status | Dependencies | Duration | Start | End
1 | Educate yourself
1.1 | Complete Trailhead modules | John | Complete | N/A | 1 day | 2015-09-15 | 2015-09-16
1.2 | Sign up for Developer Edition organization | John | Complete | N/A | 1 day | 2015-09-15 | 2015-09-16
1.3 | Read Lightning Experience book | John | Complete | N/A | 2 days | 2015-09-16 | 2015-09-18
1.4 | Review comparison charts | John | Complete | N/A | 1 days | 2015-09-16 | 2015-09-17
2 | Educate your company
2.1 | Identify executive sponsor | John | Complete | N/A | 1 day | 2015-09-17 | 2015-09-18
2.2 | Identify stakeholders | Gloria | Complete | 2.1 | 1 day | 2015-09-18 | 2015-09-19
2.3 | Conduct gap analysis | John | Complete | 2.2 | 3 days | 2015-09-17 | 2015-09-20
2.4 | Lightning Experience demo | John | Complete | 2.3 | 1 day | 2015-09-20 | 2015-09-21
2.5 | Decision point: Enable Lightning Experience? | Gloria | Complete | 2.4 | 1 day | 2015-09-23 | 2015-09-24
3 | Craft your rollout strategy
3.1 | Identify pilot group | Patrick | In progress | 2.5 | 1 day | 2015-09-24 | 2015-09-25
3.2 | Identify super users | Gloria | In progress | 2.5 | 2 days | 2015-09-24 | 2015-09-26
3.3 | Create Chatter group | John | In progress | 2.5 | 1 day | 2015-09-25 | 2015-09-26
3.4 | Identify measures for success | Patrick | In progress | 2.5 | 3 days | 2015-09-26 | 2015-09-29
3.5 | Create marketing and communication plan | Joan | In progress | 2.5 | 3 days | 2015-09-24 | 2015-09-27
3.6 | Create training plan | Joan | In progress | 2.5 | 3 days | 2015-09-24 | 2015-09-27
3.7 | Update any customizations insandbox | John | In progress | 2.3 | 3 days | 2015-09-21 | 2015-09-24
3.8 | Create test plans | John | Not yet started | 3.7 | 2 days | 2015-09-25 | 2015-09-27
3.9 | User Acceptance Testing | John | Not yet started | 3.8 | 2 days | 2015-09-28 | 2015-09-30
3.1 | UAT fixes (if any) | John | Not yet started | 3.9 | 3 days | 2015-10-01 | 2015-10-05
3.11 | Conduct survey or take snapshot | John | Not yet started | N/A | 1 day | 2015-10-04 | 2015-10-05
4 | Execute your rollout plan
4.1 | Activate super users | Joan | Not yet started | 3.2 | 14 days | 2015-10-01 | 2015-10-15
4.2 | Train users and have them do Trailhead | Joan | Not yet started | 3.6 | 5 days | 2015-10-07 | 2015-10-12
4.3 | Execute marketing and communication plan | Joan | Not yet started | 3.5 | 21 days | 2015-09-22 | 2015-11-01
5 | Enable Lightning Experience for selected users
5.1 | Go live: Complete steps to enableLightning Experience | John | Not yet started | 4.1, 4.2, 4.3 | 1 day | 2015-10-15 | 2015-10-15
6 | Measure, monitor, and iterate
6.1 | Create reports and dashboards | John | Not yet started | 5.1 | 1 day | 2015-10-14 | 2015-10-15
6.2 | Conduct business user surveys | John | Not yet started | 5.1 | 5 days | 2015-10-17 | 2015-10-21
6.3 | Set up regular meeting with super users | John | Not yet started | 5.1 | 1 day | 2015-10-27 | 2015-10-28
6.4 | Report out to executive sponsors | John | Not yet started | 5.1 | 1 day | 2015-10-31 | 2015-11-01